Breage Parish Council

Risk Management Policy (2025)

Adopted: 04 November 2025 					Review Due: November 2026

Signed: .................................................... Chair Cllr A.E. Woodhams

### 1. Purpose

This policy sets out Breage Parish Council’s commitment to managing risk in accordance with UK legislation and best practice. It aims to ensure that risks are identified, assessed, mitigated, and monitored to protect the Council’s assets, operations, reputation, and the well-being of the community.

### 2. Legal and Regulatory Framework

This policy is informed by the following legislation and guidance:

- Health and Safety at Work etc. Act 1974

- Management of Health and Safety at Work Regulations 1999

- Fire Safety (England) Regulations 2022 (fully enforced in 2025)

- Personal Protective Equipment at Work (Amendment) Regulations 2022

- ISO 31000:2018 Risk Management – Principles and Guidelines

- HM Treasury’s Orange Book (2025 edition)

### 3. Scope

This policy applies to all Council activities, including:

- Governance and decision-making

- Asset and facility management (e.g., Parish Rooms, Cemetery, Public Spaces)

- Service delivery and community engagement

- Employment and contractor management

### 4. Definitions

- Risk: The possibility of an event or condition that could negatively impact the Council’s objectives.

- Risk Management: The process of identifying, evaluating, and controlling risks.

### 5. Roles and Responsibilities

- Council: Overall accountability for risk management.

- Clerk: Maintains the risk register, coordinates assessments, and ensures compliance.

- Councillors: Participate in risk identification and mitigation.

- Contractors and Volunteers: Must comply with Council safety codes and provide relevant documentation.

### 6. Risk Management Process

#### 6.1 Identification

Risks are identified across categories:

- Physical (e.g., slips, trips, manual handling)

- Operational (e.g., lone working, overcrowding)

- Environmental (e.g., cemetery hazards, public space deterioration)

- Strategic (e.g., legislative changes)

- Compliance (e.g., fire safety, PPE provision)

#### 6.2 Assessment

Each risk is assessed using:

- Likelihood (L) and Severity (S) scores

- Priority Risk Rating (PRR) scale:

  - Immediate (24 hrs)

  - High (1 week)

  - Medium (1 month)

  - Low (12 months)

  - Insignificant (no action)

#### 6.3 Control Measures

Existing controls are documented and reviewed. Examples from the 2024–2025 assessment include:

- Fire evacuation procedures

- Lone Worker Policy

- Annual PAT testing

- Cemetery inspections and signage

#### 6.4 Additional Controls

Where gaps exist, further actions are planned, such as:

- Training in ladder use and fire extinguisher operation

- Signing of H&S annexes by contractors

- Installation of safety signage in public areas

#### 6.5 Monitoring and Review

- Risk assessments are reviewed annually or upon significant change.

- The Clerk ensures documentation is updated and distributed to relevant parties (e.g., contractors, councillors).

- Internal audits and external inspections may be used to validate controls.

### 7. Governance and Transparency

- Risk management is embedded in Council decision-making.

- Findings are recorded and shared in Council minutes.

- The Council maintains a Risk Register and updates it regularly.

### 8. Training and Awareness

- Councillors and staff receive training on risk awareness and control procedures.

- Contractors must demonstrate competence and hold valid insurance.

### 9. Continuous Improvement

- Lessons learned from incidents and audits inform future risk strategies.

- The Council remains responsive to evolving risks, including cyber threats and climate-related hazards.

Priority Risk Rating (PRR)

- Immediate Action (24 hrs)

- High Priority (1 week)

- Medium Priority (1 month)

- Low Priority (12 months)

- Insignificant Risk (no action)

- Specialised Assessment required

- Welfare (Legal requirement)

Breage Parish Council

Risk Assessment 2021

RISK ASSESSMENT

Prepared by:  David Rutherford, Parish Clerk

Next Review due: November 2026

Review Date : November 2025

| Hazard (Potential to cause harm) | Who is at risk? (inc no) | Existing Control Measures | L | S | PRR | Regulations, Guidance and Standards considered | Additional Controls Required | Target Date | RRR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PARISH ROOMS 1.Slips and Trips 2.Manual handling of office equipment 3.Display screen equipment 4.Working at height 5. Electrical 6.Fire 7.Lone Working 8.Overcrowding of meeting room | All users All users Clerical Staff Volunteers All users All users Staff and Councillors Any people present | Good housekeeping: all areas kept clear Anti-slip mats in place at entrance Staff trained in manual handling. Help sought if unable to move too heavy objects Assessments of workstation annually to ensure Staff are happy with conditions. Workstation and equipment set to ensure good posture and to avoid glare and reflections. Work planned to include change of activity. Lighting and temperature suitably controlled. An appropriate step ladder is currently in place EN131 Mark Any person to report defective plugs, discoloured sockets or damaged cables/equipment, etc. Defective equipment taken out of use if safe to do so and repaired or replaced as necessary Fire Evacuation procedure and fire extinguishers in place, signs clearly visible. Escape routes clear at all times. Extinguishers serviced annually and replaced as necessary see separate Lone Worker Policy Chairman is able close the meeting and rearrange to hold in a larger building |  |  | 4 4 4 4 4 4 4 3 | Health & Safety at Work Act 1974 BPC Safety Policy – Lone Worker Annex | Mandatory use of sack trolley for manual handling Ops to trained in ladder use Training to be organised by Clerk with immediate effect when needed PAT tested annually All councillors and clerk to know uses of different fire extinguishers. |  | 4 4 4 4 4 4 4 4 |

Copies of this risk assessment must be given to the following people:

- Parish Council

- Cleaner

- Contractors

Assessor: Cllr AE Woodhams

Date November 2025

Review date: November 2026

HH = 1  		MH = 2			LH = 4

HM = 2			MM = 3			LM = 5

HL = 3			ML = 4			LL = 5

Priority Risk Rating (PRR)

- Immediate Action (24 hrs)

- High Priority (1 week)

- Medium Priority (1 month)

- Low Priority (12 months)

- Insignificant Risk (no action)

- Specialised Assessment required

- Welfare (Legal requirement)

Breage Parish Council

Cemetery

Cemetery Risk Assessment 2021

RISK ASSESSMENT

Prepared by:  Parish Clerk October 2025

Next Review due: October 2026

| Hazard (Potential to cause harm) | Who is at risk? (inc no) | Existing Control Measures | L | S | PRR | Regulations, Guidance and Standards considered | Additional Controls Required | Target Date | RRR |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| CEMETERY 1.Slips and Trips 2.Overhanging brambles etc. around boundary 3.Badly maintained graves. 4.Unsafe Memorials 5.Cemetery safety 6. Gravedigging 7. Infectious diseases 8. Safety at interments 9. Injury to operatives, dust inhalation, being hit by projectiles when strimmers or mowers for grasscutting | All users All users All users All users All users Gravedigger All users Public Operative | Regular maintenance Boundary hedges regularly trimmed. Contractor puts date when work carried out on invoice To be reported by Cemetery Councillor after carrying out annual checks Memorials hand checked once every 5 years Unsafe memorials will be supported for one year to allow time for fixing Memorials will be laid down if no alternative 6 monthly inspections carried out and recorded by Cemetery Councillor Safety Code Annex 7 Signs to be in place stating danger of potential infections and to wash / sanitise hands after visit. Cemetery councillor or clerk attends internment BPC Safety Code Grass cutting –Annex 2 – to be agreed and signed by Contractor who must hold Public Liability Insurance Documents are checked when contracts are signed Fuelled prior to starting Stones, dog faeces removed Contaminated clothes to be removed and bagged |  |  | 3 3 4 4 3 3 4 4 4 | BPC Safety Policy Annex 3 BPC Cemetery Health & Safety Policy BPC Cemetery Health & Safety Policy BPC Cemetery Health & Safety Policy BPC Safety Code Grass Cutting, Annex 2. | Cemetery H&S Policy and H&S Annexes 2,3,6,7 to be signed by Gravedigger Cemetery H&S Policy to be signed by Cemetery councillor and clerk Copies of PL Insurance Documents to be given to BPC when contracts signed. Contractor risk assessments to be reviewed. |  | 4 4 4 4 4 4 4 4 4 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Priority Risk Rating (PRR)

- Immediate Action (24 hrs)

- High Priority (1 week)

- Medium Priority (1 month)

- Low Priority (12 months)

- Insignificant Risk (no action)

- Specialised Assessment required

- Welfare (Legal requirement)

Breage Parish Council

Public Spaces Risk Assessment 2021

RISK ASSESSMENT

| Hazard (Potential to cause harm) | Who is at risk? (inc no) | Existing Control Measures | L | S | PRR | Regulations, Guidance and Standards considered | Additional Controls Required | Target Date | RRR | RRR |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BREAGE FIELD 1.Hazards arising during maintenance work 2.Hazards arising from discarded items Slips and Trips 3.Injury from play equipment 4.Members of the public climbing hedges to access field, knocking stones from hedges 5.Roads border the Playing Field and gates open on to road ASHTON AMENITY AREA PLAY AND EXERCISE EQUIPMENT 1.Hazards arising during maintenance work 2.Hazards arising from discarded items Slips and Trips 3.Injury from play equipment PRAA SANDS EXERCISE & BASKETBALL EQUIPMENT 1.Hazards arising from discarded items Slips and Trips 2.Injury from equipment PRAA GREEN 1.Injuries caused to walkers Slips and Trips 2.Injury from deteriorating metal posts/signs/chains, fences, etc. 3.Injury from damage caused to granite benches 4.Injury from holes in the Green caused by dogs and rabbits FOOTPATHS, BRIDLEWAYS, STILES & SWCP Specifically assigned to Breage Parish Council from LMP & SWCP schedules 1.Hazards arising during maintenance work NOTICE BOARDS/BENCHES 1.Hazards arising from unlawful damage and wear | All users All users All users All users All users All users All users All users All users All users All users All users All users All users All users All users | Safety Code is agreed and signed by Contractors Playing Field Committee and Councillor G Smith to inspect field and keep clear of discarded items Record should be kept of dates and of findings Public Liability Insurance held Monthly safety check by RoSPA Qualified inspector and necessary repairs by South West Playground Safety Inspections Documentation to Council Notice erected on hedge Wooden barrier has been installed Safety of hedges regularly checked by Contractor whilst trimming and problems reported to Clerk Metal barred safety barrier erected at in September 2011 and second barrier December 2019 Safety catches on gates Safety Code is agreed and signed by Contractors Ashton Village Committee has Land Useage Agreement Members and Cllrs Bradford to inspect field and keep clear of discarded items Record should be kept of dates and of findings Public Liability insurance held Monthly check by RoSPA Qualified inspector and necessary repairs by South West Playground Safety Inspections. Documentation to Council Cllr Southam to inspect and report to Clerk Public Liability insurance held Monthly check by RoSPA Qualified inspector and necessary repairs by South West Playground Safety Inspections Safety Code is agreed and signed by contractors. Should be checked once a month by Cllr Southam problems reported to Council Should be checked once a year for deterioration and problems reported to Council Cllr Southam to check Checked by Handyman twice a year Holes should be filled with soil, sand and ash and should be checked once a year for deterioration by Cllr Southam Safety Code is agreed and signed by contractor Checked 6 monthly by Handyman and reported to Clerk |  |  | 4 4 2 4 4 4 4 2 4 2 3 4 4 3 3 4 |  | Add sign saying “Beware Road” |  | 4 2 3 4 4 4 2 3 2 3 2 4 4 3 4 4 |  | 4 2 3 4 4 4 2 3 2 3 2 3 2 4 4 3 4 4 |  |